Instructions:

This checklist is available to be used as a guide by Finance Advisory staff in working through the process of closing out projects.

| No. | Steps | Check |  |  |
| --- | --- | --- | --- | --- |
|  |  | Y | N | N/A |
| Financial Project Close-out Preparation |  |  |  |  |
|  | Is the project approaching or past its end date? If no, STOP If yes, go to Step 2 |  |  |  |
|  | Does the project end date require variation? If yes, advise Chief Investigator to consult with Research office and initiate GRL re-record process if necessary If no, go to Step 3 |  |  |  |
|  | Are there outstanding project commitments in the Transaction Details Report? Have you actioned and cleared the outstanding commitments |  |  |  |
|  | Are there transactions in the project accounts? If no, STOP as project will be closed automatically by central Contracts & Grants Accounting. If yes, go to Step 5 |  |  |  |
|  | Are there balances on the fund, function or site codes? If yes, process correcting journal between these codes If no, go to Step 6. |  |  |  |
|  | Is the remaining project balance a small balance (<$200, unless $200 is material to the project)? If yes, check that there are no sub-ledger transactions and process correcting journal to clear balance to the central operating account 592310. Notify central Contracts & Grants Accounting to close project. If no, go to Step 7 |  |  |  |
| Review of Project Surplus/Deficit and Final Close |  |  |  |  |
|  | Have all valid costs been charged to the project as per contract conditions? If no, check post-end date expenses, check with CI, process journal (with CI approval and supporting documents) to transfer valid and substantiated costs into project If yes, go to Step 8 |  |  |  |
|  | Is there a deficit? If yes, process adequately substantiated journal (with CI approval and supporting documents) to transfer costs out of project to Operating, AC&A or another project per applicable expenditure line item (for errors, under-budgeting). If no, go to Step 9 |  |  |  |
|  | Have operational milestones been achieved? If no, consult with Chief Investigator, Research Office to initiate GRL re-record process if necessary If yes, go to Step 10 |  |  |  |
|  | Determine whether UQ is contractually required to refund any surplus through review and advice of: - Project Details Report - Refund Clause (“Y/N”) captured by Contracts and Grants Accounting on initial review of contract. - Contract - Consult UQ Legal NewMatters@research.uq.edu.au for advice if uncertain and if Project Details Report - Refund Clause reflects a “N” If yes, advise central Contracts & Grants Accounting team to request an invoice from the funding provider If no, depending on research subsidisation and operating funding position, process a journal to transfer surplus to Operating account 592310 or AC&A (restricted fund code), with the approval of the Head of School |  |  |  |
|  | Is the project balance nil? If no, there is likely an error in closing entries - go back and check journals If yes, go to Step 12 |  |  |  |
|  | Are there any outstanding financial statements or other reporting obligations? If yes, provide CGA with a sign-off form for the project GL numbers (Final Acquittal Statements only) and request central Contracts & Grants Accounting to prepare the Financial Statements If no, notify central Contracts & Grants Accounting to close project |  |  |  |